## Dashboard
DSCR Lead Gen — Project Status Dashboard
Last updated: March 6, 2026 ¦ Zack / CrossCountry Mortgage
QUICK STATS
Total Leads (PB + Broward) | 7,537
Phones Found | 3,143 (42%)
Emails Found | 2,592 (34%)
Total Spent | $71.50
Remaining to Launch | $12 — $75
Airtable Tables Built | 7/7
Airtable Fields Built | 193/193
Broken Formulas/Rollups | 0
Pipeline Scripts Built | 17
Scripts Production-Ready | 8 of 17

## Airtable CRM
Phase | Task | Status | Time Est. | Who | Notes
Phase 1 | Delete Table 8 | NOT DONE | 1 min | Zack | Manual in Airtable UI — click tab dropdown > Delete
Phase 1 | Rename "Trigger County" → "Trigger Count" | NOT DONE | 1 min | Zack | Properties table — Edit field name
Phase 1 | Add Estimated Annual Rent formula | DONE | - | - | Confirmed via API — field exists on Properties
Phase 1 | Add Property Count rollup to Entities | DONE | - | - | Confirmed via API — 19 fields on Entities
Phase 2 | Create 6 Investor views | NOT DONE | 8 min | Zack | Tier 1, Tier 2, Follow-Up Due, DNC, New Leads, Gallery
Phase 2 | Create 3 Properties views | NOT DONE | 4 min | Zack | Cash Purchase, By Investor, Low DSCR
Phase 2 | Create 6 Financing views | NOT DONE | 8 min | Zack | Maturity, High Rate, Hard Money, Balloon, Prepay, Refi Score
Phase 2 | Create 4 Opportunities views | NOT DONE | 5 min | Zack | Kanban, Active Pipeline, Closing This Month, Stale Deals
Phase 2 | Create 3 Outreach Log views | NOT DONE | 3 min | Zack | Today, This Week, By Investor
Phase 2 | Create 2 Compliance views | NOT DONE | 2 min | Zack | Overdue DNC, Consent Records
Phase 3 | Auto 1: Hard Money → Opportunity | NOT DONE | 3 min | Zack | When Financing.Hard Money Flag is not empty → Create Opportunity
Phase 3 | Auto 2: Maturity → Opportunity | NOT DONE | 2 min | Zack | When Financing.Maturity Window Flag → Create Opportunity
Phase 3 | Auto 3: Cash Purchase → Opportunity | NOT DONE | 2 min | Zack | When Properties.Cash Purchase Flag → Create Opportunity
Phase 3 | Auto 4: Follow-Up Reminder email | NOT DONE | 2 min | Zack | When Outreach Log.Follow Up Date = today → email
Phase 3 | Auto 5: DNC Scrub Overdue alert | NOT DONE | 2 min | Zack | When Compliance.Scrub Overdue → email
Phase 3 | Auto 6: Stale Deal alert | NOT DONE | 2 min | Zack | When Opportunities.Days in Stage > 14 → email
Phase 3 | Auto 7: Update Last Contact Date | NOT DONE | 2 min | Zack | When Outreach Log created → update Investor
Phase 3 | Auto 8: New Lead DNC reminder | NOT DONE | 2 min | Zack | When Investor created → create Compliance record
Phase 4 | Upload test_investors.csv | NOT DONE | 3 min | Zack | Import CSV → map columns → import
Phase 4 | Upload test_entities.csv | NOT DONE | 3 min | Zack | Map Investor (Owner) to existing records by Full Name
Phase 4 | Upload test_properties.csv | NOT DONE | 3 min | Zack | Map Owner Investor + Owner Entity linked fields
Phase 4 | Upload test_financing.csv | NOT DONE | 3 min | Zack | Map Property linked field by Property Address
Phase 4 | Validate triggers fire correctly | NOT DONE | 5 min | Zack | Check Hard Money/High Rate flags, Lead Scores, auto Opportunities
Phase 5 | Build Daily Command Center interface | NOT DONE | 15 min | Zack | Pipeline value, follow-ups, top leads
Phase 5 | Build Investor Profile interface | NOT DONE | 15 min | Zack | Single investor detail view
Phase 5 | Build Pipeline Manager interface | NOT DONE | 10 min | Zack | Kanban + deal metrics
Phase 5 | Build Trigger Alert Center interface | NOT DONE | 10 min | Zack | All trigger flags in one place
Phase 6 | Prepare full 7,500 lead CSVs | NOT DONE | 30 min | Claude | Transform pipeline output → Airtable import format
Phase 6 | Full import (Investors → Entities → Properties → Financing) | NOT DONE | 30 min | Zack | Upload in order, map linked fields
Phase 6 | HubSpot Free + Zapier sync | NOT DONE | 60 min | Zack | Sync Tier 1/2 prospects for outreach sequences

## Pipeline Scripts
Script | Name | Status | Completeness | Blockers | What It Does | Next Action
01 | Download NAL | DONE | 100% | None | Download FDOR property data | N/A
02 | Parse NAL | DONE | 100% | None | Parse & standardize property data | N/A
03 | Filter ICP | DONE | 100% | None | Score 0-100 and tier leads | N/A
04 | SunBiz Resolve | DONE | 100% | Cloudflare blocks | LLC → person name resolution | N/A
05 | Enrich Contacts | DONE | 100% | None | Contact enrichment + research tracker | N/A
05b | Merge Enrichment | DONE | 100% | None | Merge Tracerfy + DBPR + SunBiz | N/A
06 | Validate Contacts | NEEDS TEST | 95% | API keys (MV + Twilio) | Email/phone validation + DNC check | Buy MV credits ($11.90), test with merged data
07 | Export Campaign | NEEDS TEST | 95% | Needs validated data | Export to Instantly/SMS/mail/Apollo formats | Run after script 06 completes
08 | Tracerfy Skip Trace | DONE | 100% | None | Skip trace 7,537 leads → 2,880 matches | N/A — $57.60 spent
10 | Apollo Enrich | DONE | 100% | Returns nothing | B2B enrichment (useless for LLC investors) | CANCEL Apollo ($99/mo savings)
11 | County Clerk | STUB | 60% | Playwright + reCAPTCHA | Scrape mortgage/lien records | Install Playwright, test 5 records manually
12 | Purchase History (SDF) | STUB | 85% | SDF download needed | Full purchase timeline per investor | Download SDF files, test parsing
13 | Rental Estimates | STUB | 70% | HUD FMR download | Rent estimates by ZIP + bedroom count | Download HUD data, test matching
14 | Wealth Signals | STUB | 70% | FEC/990 API wrappers | Political donations, board seats, other LLCs | Complete FEC API integration
15 | Network Mapping | STUB | 50% | Logic incomplete | Co-investors, shared PMs, agents | Build matching logic
16 | Life Events | STUB | 40% | Depends on script 11 | Divorce, liens, lis pendens, probate | Complete after script 11 works
20 | Build Dossier | STUB | 50% | Depends on 11-16 | Assemble full investor profiles | Complete after all intelligence scripts

## Blockers & Spend
Item | Cost | Status | Priority | Action Required
DNC Scrub (legally required) | $0 — $63 | BLOCKING | CRITICAL | Option A: Free FTC registry (federal only). Option B: Tracerfy DNC $63 (federal + state + TCPA litigators). MUST do before ANY phone outreach.
MillionVerifier credits (email validation) | $11.90 | BLOCKING | HIGH | Buy 5,000 credits at millionverifier.com. Current 2,000 exhausted.
FTC DNC Registry (area codes 561, 954, 305, 786) | $0 | IN PROGRESS | CRITICAL | Register at telemarketing.donotcall.gov. First 5 area codes free.
Cancel Apollo.io | $0 (saves $99/mo) | DECISION | MEDIUM | Returns nothing for LLC investors. Tracerfy works. Cancel to save $99/mo.
Datazapp second-pass | $50 top-up + $75 balance | OPTIONAL | LOW | For 3,557 Tracerfy misses. Not urgent — focus on matched leads first.
FL Telemarketing License | Varies | VERIFY | HIGH | Verify CCM holds license before phone outreach at scale. $1,500/yr + $50/person + $50K bond.
Airtable Team plan | $20/seat/mo | VERIFY | MEDIUM | Needed for >1,200 records. Required before 7,500 lead import.
SPEND SUMMARY
Tracerfy skip trace | $57.60 | PAID
Twilio phone validation | $9.00 | PAID
MillionVerifier (2K credits) | $4.90 | PAID
TOTAL SPENT | $71.50
MillionVerifier top-up (5K) | $11.90 | NEXT
Tracerfy DNC scrub | ~$63.00 | DECIDE
TOTAL REMAINING | $12 — $75

## Airtable API Audit
Table | Field Count | Expected | Match | Formulas | Rollups | Broken | Record Count
Investors | 50 | 50 | YES | 9 | 10 | 0 | 0
Ownership Entities | 19 | 18 | +1 | 1 | 4 | 0 | 0
Properties | 37 | 36 | +1 | 11 | 3 | 0 | 0
Financing | 35 | 35 | YES | 11 | 0 | 0 | 0
Compliance | 15 | 15 | YES | 2 | 0 | 0 | 0
Opportunities | 24 | 24 | YES | 5 | 0 | 0 | 0
Outreach Log | 13 | 13 | YES | 0 | 0 | 0 | 0
VERDICT: Base is structurally complete. 0 broken formulas/rollups. All 7 tables present.